## Ongoing Projects
Company Name | Current Action Item | Project Status | tNDA | Last Update made | Application Description
Aspero | Testing Silq Treated Samples | Performance Testing | Signed | 2026-06-09 | Endoscope Tubing
AB | Silq Performing Electrochemical Testing | Electrochemical analysis, performance testing starting Q3 | Signed | 2026-06-02 | Cochlear Implants
BMC Health | Regulatory Discussions | Feasibility Complete, samples remain | Signed 2/16/26 | 2026-06-01 | Penile Implant
Medtronic | MTA In Development | Initiated |  | 2026-06-01 | Hydrocephalus Shunt
Boston Scientific (Ireland) | NDA in Development | Initiated |  | 2026-06-01 | Urology Device
Establishment Labs | Nusil to Coordinate TNDA | Very interested, but cash constrained |  | 2025-09-12 | Breast Implants
Abbott | Silq to treat 20cm Samples and invoice work |  | Signed | 2025-09-05
Med-El | Eugiene to follow up upon return | Pre-NDA Samples Sent 8.12.25 |  | 2025-08-15
GC Aesthetics | GC to Review Proposal | Feasibility quote sent with biological testing | Signed | 2025-07-18 | Breast Implants
Todoc |  | Todoc are evaluating their resource availablity for this project | Sent June 9 '25 | 2025-07-01 | Cochlear Implants
Silimed | NDA under review | Meeting with distributor in Brazil - setting up additional SIlq introductory meetings |  | 2025-07-01
Abbvie | Project transitioning to Costa Rica team | 3-way NDA signed 6/30/25 | Signed | 2025-06-30 | Tissue Expander Component
Sophysa |  | Awaiting decision on their part on NDA/TNDA signature |  | 2025-01-31 | Hydrocephalus Shunt
Gulf Rubber |  | Awaiting Nusil follow up on introductory call | Signed | 2025-01-28
Pelican Health |  | NDA Sent |  |  | Digestive sampling device

## Currently Stalled Projects
Company Name | Project Status | Application Description | Last Contact Date
Procope Medicals | project stalled due to other priorities in house, research should resume in next couple months | total artificial heart | 2025-03-13
Mitka
BSC (via Nusil)
J&J (via Nusil)
Edwards Life Sceinces
Luna
Newronika | quote was sent to them but fell through |  | 2024-10-25
Becton Dickenson
Perikinetics | Focused on alternative design priority | artificial pancreas for insulin therapy. Insulin denaturing, foreign body response, catheter occlusion (collagen) | 2021-10-05
Nurotron | last discussed feasibility testing on coated electrodes | Cochlear Device | 2022-05-16
Freudenberg (inhealth) |  | Voice Prosthesis
Microport | Not seeking novel technology, only small iterative improvements | Pacemaker | 2023-11-10
MED-EL | not seeking new filing of devices yet, might be intersted for new devices later on | cochler devices | 2025-06-02
Polytech | were not interested when contacted | BIs | 30/06/2024
Vygon | TNDA sent for approval 4/2 to not restrict to any geography. Preliminary silicone CVC samples to be provided for evaluationent for approval. Decided not to pursue | Catheters | 2025-04-02 | Catheters
Tingo
Cochlear Australia | Brian provided ASTM Test Results. Awaiting their response on next steps. Silq to provide summary document describing deposition procedure to their devices | Cochlear Implants | 2025-02-12
Next Step/Visionair | Simulated Mucus recieved 3/12. Feasability testing difficult for their specific purpose | Signed | 2025-05-14
HPBio | Customer decided to stay with method of dipping the device in an active. |  | 2026-03-26
New World | Pricing discussion 9/30/25. Aging Samples Finishing 8/30. Nylon Feasability Completed. & Dedicated Fixture proposal approved | Glaucoma Treatment Drain | 2025-09-12

## Potential Targets
Company | Notes | Challenge | Application | Device Details
J&J | Baerveldt nonvalved Implant J&J | Occlusion, infection, bleeding, hypontony | glaucoma implants | Silicone device includes holes to allow fibrous tissue growth
Glaukos Corp. |  |  | glaucoma implants
Myra Medical |  |  | glaucoma implants
HPBio (Brazil) | Looking to schedule call in Nov. |  |  | Neurosurgical (Drains, shunts), Gastroenterology (feeding catheter, silicone)
LifeSil (Brazil) | Looking to schedule call. |  | Breast Implants.
FCI (France) |  |  | Ocular
Aspero Medical | Active Project | Lubiricity on inside of Endoscopic Sleeve device | Endoscopic
Ventura Biomedica | Scheduling call |  | Hydrocephalous | ventricular catheters
Kerecis | Scheduling call |  | Wound management | Fish skin based skingrafts
Cirtec | Intro call on 2/12/26 |  | Various | Catheters and various other HC/MI devices
BMC | Meeting at MD&M. Callon 2/12/26 | Fibrosis and friction | Penile implant
Nexsilis
Medicone (Brazil)
Silimed (Brazil)
FAJ (Brazil)
IBEG (Brazil)
Gabisa
Faga Medical (Brazil) |  |  | Breast Implants. | Breastimplant with PU foam setcion. May want echogenic silicone
Medtronic
Osstem Implant (Korea)
BS Research (Korea)
Hans Biomed (Korea)
Boston Scientific (Ireland)